## Slide 1: Citi Salutes Community Challenge
Financial Education Program with Combat2College
Quinton Carter, Jordan Alvarado
August 15, 2017

## Slide 2: Table of Contents
Project Outline
Budget
Combat2College Overview
Project Roadmap
Veteran’s Personal Finance Handbook Outline

## Slide 3: Project Outline
Veteran Personal Finance Handbook
  Provide Veterans with tailored personal finance recommendations
  Distributed by Combat2College at local university Veteran Study Centers and Community Engagement events (with help from Citi Volunteers)
Veteran Personal Finance Presentations
  Presented at Veteran Study Centers and/or Citi Site
  Recurring presentations during Fall and Spring Semesters
  Presenters will be Citi Volunteers
  Presentation will review the handbook and hold Q&A
Veteran Scholarship and Challenge Grants
  $5,000 scholarship presented at a Jacksonville Sporting Event by Citi and Combat2College Leaders to Veteran that has demonstrated financial need and commitment to financial self-empowerment and growth
  Challenge Grants will be divided into $250 mini grants and presented to winners of the following challenges designed to demonstrate knowledge gained from financial education presentations
    Essay Challenge – Ex. “Why is financial empowerment important?”
    Budget Challenge – Using the handbook as a guide, outline a 1-5 yr personal budget plan of action
Finance Education Library
  Funds used to purchase finance related course materials to be stored at the Study Centers and loaned to veterans enrolled in those courses
  Wall Street Journal subscription (1yr) provided to Study Centers
Online Skills Development Courses
  Courses will be accessible through the C2C website and the Veteran Study Center computers
    Finance and Accounting Courses
    Job Skills Preparation Courses (Resume Builder, Interview preparation, etc.)
    Personal Well-Being Courses

## Slide 4: Project Budget
Award Breakdown $10,000
Project Funding Breakdown By Initiative
Chart: 
| Veteran Scholarship | Finance Education Library | Finance Education Challenge Grants | Veteran Personal Finance Handbook | Online Skills Development Courses
Series 1 | 0.5 | 0.2 | 0.2 | 0.06 | 0.04
 | Total Amount | Allocated Amount Details
Veteran Scholarship | $5,000 | Will support a Veteran who has demonstrated financial need Student veteran is currently working towards a finance related degree
Finance Education Library | $2,000 | Average book costs are $80 per credit hour at FSCJ Most books are custom for University ranging from $80-$250+ each 1 year WSJ subscription = $169.99
Finance Education Challenge Grants | $2,000 | Broken into $250 grants for winners of Essay and Budget Challenges Provide aid to 8 local Veterans Contestants demonstrate financial knowledge
Veteran Personal Finance Handbook | $600 | 8 to 10 page handbook - Print color, front and back - $0.30 cost per page (Personal rate) = $30 for 100 Print color, front and back - $0.03 per page (Business rate) = $300 for 100 Staple binding - $0
Online Skills Development Courses | $400 | Skill success - $10 to $200 each Udemy courses - $20 to $200 each Code academy Brain fuse

## Slide 5: Combat2College Overview
Combat2College assists Veterans and their families during the transition from military service to college student
  Primary goal is the successful academic advancement post-separation from the military
  Combat2College team is made up of all volunteers(?)
  Established in 2012
  501(c) Registered?
The C2C team takes pride in knowing that nearly 100% of every dollar raised goes to local veterans in need
  Provided $___ to veterans in need
  Supported nearly 150 veterans to date
Examples of the guidance and support provided to veterans
  Financial Support (Scholarships & Stipends)
  School/Work/Life Balance (Time Management, Study Skills, Mentoring, etc.)
  Community Involvement (Sponsored Veterans Programs, Informational Workshops, etc.)
  Job Placement (Resume Building, Personal Identity Exploration, Interview Preparation)
  Operate 2x Veteran Study Centers at Florida State College Jacksonville’s North and South campuses

## Slide 6
Project Roadmap
Your Logo
Nov ’17
Dec ‘17
Jan ‘18
Feb ‘18
Mar ‘18
Finalize Handbook Design & Vetting
Complete information gathering, review with Citigold advisor, legal and PR review
(Completion target – end of Q4 ‘18)
Handbook Printing & Distribution
Print through Citi print services and distribute to Combat2College Veteran Study Centers
Develop ‘Wish List’ and prioritize purchases. (Includes online courses)
Identify Financial Education Library Resources
Purchase & deliver library resources; Activate print and online subscription services (online courses, WSJ, etc.)
Establish Financial Education Library
Financial Education Presentation
Present Scholarship Award
Presented at a Jacksonville professional sporting event

## Slide 7: Veteran’s Personal Finance Handbook Outline
Comparison of recurring bills while on active duty service versus as a veteran (1 page)
  New Bills – Rent, Electric, Water, Gas (previously covered by DoD for those service members living in barracks on base)
Retirement Accounts / Savings / Investments (1-2 pages)
  401(k)
  Roth IRA
Paying for College (1-2 pages)
  GI Bill – the benefits and how it works
  Scholarships / Grants – Where to find and how to apply
  Student Loans – FAFSA, How they work, Subsidized versus unsubsidized
Buying a House (1-2 pages)
  Mortgage Options
    VA Loan – the benefits and how it works
  Homeowners Insurance
  HOAs
  Utilities
  Taxes
Health Insurance / HAS (1 page)
Best Practices for Budget Management (1 page)
  60% of income – Living Expenses
  20% - Savings
  15% - Debt Payment
  5% - Entertainment/Free Spend